# AVP - GO-LIVE-PLAN

# AVP Go-Live Plan

From Zero to Production: Complete Deployment, Rollout, and Launch Strategy

Version: 1.0-draft Date: 2026-03-18

## Table of Contents

- Executive Summary

- Phase Overview

- Phase 1: Foundation

- Phase 2: Alpha Network

- Phase 3: Beta Launch

- Phase 4: Public Launch

- Phase 5: Scale

- Infrastructure Requirements

- Team Requirements

- Budget Estimation

- Risk Mitigation

- Success Metrics

## 1. Executive Summary

The AVP Go-Live Plan outlines a 12-month journey from protocol specification to public launch, followed by a scaling phase in year 2. The approach is:

- Build the protocol + reference implementation (3 months)

- Seed the network with hand-picked vendors (3 months)

- Open beta with real transactions (3 months)

- Public launch with self-service onboarding (3 months)

- Scale to 1000+ vendors (Year 2)

## 2. Phase Overview

Month:  1   2   3   4   5   6   7   8   9   10  11  12  ...
        ├───┼───┼───┤───┼───┼───┤───┼───┼───┤───┼───┼───┤
Phase:  │ FOUNDATION  │ ALPHA       │ BETA        │ LAUNCH  │ SCALE
        │             │ NETWORK     │             │         │
        │             │             │             │         │
Build:  │ Protocol    │ SDKs v1     │ Dashboard   │ Self-   │ Marketplace
        │ Spec v1     │ Registry v1 │ Chrome Ext  │ service │ API economy
        │ Auth layer  │ Trust v1    │ Integrations│ v1      │ Ecosystem
        │ Ref impl    │             │             │         │
        │             │             │             │         │
Users:  │ 0           │ 10-20       │ 50-100      │ 500+    │ 1000+
        │             │ vendors     │ vendors     │ vendors │ vendors
        │             │ 5 buyers    │ 20 buyers   │ 100+    │
        │             │             │             │ buyers  │

## 3. Phase 1: Foundation (Months 1-3)

### 3.1 Objectives

- Finalize protocol specification v1.0

- Build reference implementation (Node.js)

- Set up core infrastructure

- Establish governance

### 3.2 Deliverables

| Week | Deliverable | Owner |
| --- | --- | --- |
| 1-2 | Protocol spec v1.0-draft published | Protocol Lead |
| 2-3 | Ed25519 auth implementation | Security Lead |
| 3-4 | Vendor SDK (Node.js) — basic | Backend Lead |
| 4-5 | Buyer SDK (Node.js) — basic | Backend Lead |
| 5-6 | Registry service — MVP | Backend Lead |
| 6-7 | Discovery document serving | Backend Lead |
| 7-8 | Handshake + RFP flow working end-to-end | Full Team |
| 8-9 | Basic proposal response flow | Full Team |
| 9-10 | Negotiation state machine | Backend Lead |
| 10-11 | Docker-based local development environment | DevOps |
| 11-12 | Integration tests + CI/CD pipeline | QA + DevOps |

### 3.3 Technical Setup

Infrastructure (Month 1):

├── GitHub Organization: github.com/avp-protocol
│   ├── avp-spec          (Protocol specification)
│   ├── avp-vendor-sdk    (Vendor SDK - Node.js)
│   ├── avp-buyer-sdk     (Buyer SDK - Node.js)
│   ├── avp-registry      (Registry service)
│   ├── avp-trust         (Trust authority)
│   ├── avp-examples      (Example implementations)
│   └── avp-website       (Protocol website)
│
├── Domain: avp-protocol.org
│   ├── Main website
│   ├── registry.avp-protocol.org
│   └── docs.avp-protocol.org
│
├── Cloud: AWS (primary) + Cloudflare (CDN/edge)
│   ├── EKS cluster (staging)
│   ├── RDS PostgreSQL
│   ├── ElastiCache Redis
│   └── S3 (documents, schemas)
│
└── CI/CD: GitHub Actions
    ├── Lint + test on PR
    ├── Build + deploy on merge
    └── Schema validation

### 3.4 Exit Criteria

- Two agents can discover each other, handshake, exchange RFP/proposal

- Auth layer passes security review

- Documentation is complete and published

- Local development environment works in < 10 minutes setup

## 4. Phase 2: Alpha Network (Months 4-6)

### 4.1 Objectives

- Onboard 10-20 hand-picked vendor companies

- Onboard 5 buyer companies

- Validate protocol with real-world usage

- Iterate based on feedback

### 4.2 Vendor Onboarding Strategy

Target: 10-20 companies that are:

- Mid-size software development companies (50-500 employees)

- Have an online presence with clear service offerings

- Open to innovation and new channels

- In the target domains: Java, travel, e-commerce, fintech

Onboarding Process:

Week 1: Outreach
│
├── Personal email/LinkedIn to CTO/VP Engineering
├── Pitch: "Be first to adopt AI vendor discovery protocol"
├── Incentive: Free premium verification for 1 year
│
▼
Week 2: Demo
│
├── Live demo of protocol in action
├── Show competitor adoption (social proof)
├── Explain zero cost, open-source
│
▼
Week 3: Integration Support
│
├── Dedicated engineer helps integrate
├── 30-minute setup call
├── Custom configuration assistance
│
▼
Week 4: Go-Live
│
├── Agent live and discoverable
├── First test RFP received
├── Feedback collected

### 4.3 Alpha Deliverables

| Week | Deliverable |
| --- | --- |
| 13-14 | Vendor onboarding portal |
| 14-16 | Assisted integration for first 5 vendors |
| 16-18 | Python SDK (vendor) |
| 18-20 | Basic web dashboard (vendor) |
| 20-22 | Buyer web dashboard (MVP) |
| 22-24 | First real RFP-to-proposal cycle completed |

### 4.4 Exit Criteria

- 10+ vendors with live agents

- 5+ real RFP-to-proposal cycles completed

- Response time SLA met (< 4 hours)

- Zero critical security issues

- Protocol spec updated based on alpha feedback

## 5. Phase 3: Beta Launch (Months 7-9)

### 5.1 Objectives

- Launch Chrome extension (beta)

- Open self-service vendor registration

- Implement trust/verification system

- Build integrations (Slack, CRM)

### 5.2 Beta Deliverables

| Week | Deliverable |
| --- | --- |
| 25-27 | Chrome extension v0.1 (invite-only beta) |
| 27-28 | Self-service vendor registration portal |
| 28-30 | Business verification pipeline |
| 30-32 | Trust score v1 implementation |
| 32-34 | Slack integration |
| 34-35 | Salesforce/HubSpot integration |
| 35-36 | Proposal comparison UI |

### 5.3 Beta User Acquisition

Target: 50-100 vendors, 20 buyers

Channels:
├── Product Hunt beta listing
├── Dev community posts (Reddit, HN, Dev.to)
├── Direct outreach to software companies
├── Partnerships with Clutch/GoodFirms
├── Webinars: "The Future of B2B Vendor Discovery"
└── GitHub stars + community building

### 5.4 Exit Criteria

- 50+ vendors registered

- 20+ buyers using Chrome extension or dashboard

- 50+ proposals generated and delivered

- Business verification processing < 5 business days

- Trust scores calculated for all active vendors

- Chrome extension stable with < 1% crash rate

## 6. Phase 4: Public Launch (Months 10-12)

### 6.1 Objectives

- Public launch of all components

- Press/media coverage

- Self-service everything

- Monetization pilot

### 6.2 Launch Deliverables

| Week | Deliverable |
| --- | --- |
| 37-38 | Chrome extension on Chrome Web Store |
| 38-39 | Public registry with search |
| 39-40 | Full documentation site |
| 40-41 | Launch marketing campaign |
| 41-42 | Monetization: premium listings pilot |
| 42-44 | WordPress plugin launch |
| 44-48 | Embeddable widget launch |

### 6.3 Launch Campaign

Pre-Launch (2 weeks before):
├── Teaser on social media
├── Blog post: "Introducing AVP"
├── Reach out to tech journalists
└── Prepare Product Hunt launch

Launch Day:
├── Product Hunt launch
├── Hacker News submission
├── Blog post + technical deep-dive
├── Twitter/LinkedIn campaign
├── Email to all beta users
└── Press release

Post-Launch (2 weeks after):
├── Respond to community feedback
├── Fix critical bugs (expected)
├── Follow-up blog posts
├── User testimonials
└── Case study: "First deal closed via AVP"

### 6.4 Exit Criteria

- 500+ registered vendors

- 100+ active buyers

- 100+ proposals per month

- First revenue generated

- Protocol spec v1.0 stable published

- Community > 1000 GitHub stars

## 7. Phase 5: Scale (Year 2)

### 7.1 Growth Targets

| Metric | Q1 Y2 | Q2 Y2 | Q3 Y2 | Q4 Y2 |
| --- | --- | --- | --- | --- |
| Registered vendors | 1,000 | 3,000 | 7,000 | 15,000 |
| Active buyers | 500 | 1,500 | 4,000 | 10,000 |
| Monthly proposals | 500 | 2,000 | 8,000 | 25,000 |
| Monthly revenue | $5K | $20K | $80K | $200K |

### 7.2 Scale Initiatives

- Regional expansion — EU, India, Southeast Asia registries

- Industry verticals — Healthcare, fintech, logistics specialization

- API economy — Third-party apps built on AVP

- Enterprise tier — Dedicated infrastructure for large buyers

- AI improvements — Better matching, negotiation, and pricing AI

- Mobile app — Native iOS/Android buyer app

## 8. Infrastructure Requirements

### 8.1 Phase-wise Infrastructure

| Phase | Compute | Database | Monthly Cost |
| --- | --- | --- | --- |
| Foundation | 2 VMs (staging) | RDS micro | ~$200 |
| Alpha | 4 VMs (staging + prod) | RDS small | ~$800 |
| Beta | K8s cluster (8 nodes) | RDS medium + Redis | ~$3,000 |
| Launch | K8s cluster (16 nodes) | RDS large + Redis cluster | ~$8,000 |
| Scale | Multi-region K8s | Multi-region DB + CDN | ~$25,000+ |

### 8.2 Production Architecture

┌──────────────────────────────────────────────┐
│           Cloudflare (Edge)                    │
│  CDN + WAF + DDoS + Rate Limiting            │
└────────────────────┬─────────────────────────┘
                     │
┌────────────────────▼─────────────────────────┐
│           AWS (Primary Region)                │
│                                               │
│  ┌─────────────────────────────────────────┐ │
│  │ EKS Cluster                              │ │
│  │  ┌────────┐ ┌────────┐ ┌────────┐      │ │
│  │  │Registry│ │Trust   │ │Search  │      │ │
│  │  │Service │ │Service │ │Service │      │ │
│  │  └────────┘ └────────┘ └────────┘      │ │
│  │  ┌────────┐ ┌────────┐ ┌────────┐      │ │
│  │  │Webhook │ │Auth    │ │Verify  │      │ │
│  │  │Service │ │Service │ │Service │      │ │
│  │  └────────┘ └────────┘ └────────┘      │ │
│  └─────────────────────────────────────────┘ │
│                                               │
│  ┌────────────┐ ┌───────────┐ ┌───────────┐ │
│  │ RDS        │ │ ElastiCache│ │ OpenSearch│ │
│  │ PostgreSQL │ │ Redis     │ │ (Search)  │ │
│  └────────────┘ └───────────┘ └───────────┘ │
│                                               │
│  ┌────────────┐ ┌───────────┐               │
│  │ S3         │ │ SQS       │               │
│  │ (Storage)  │ │ (Queues)  │               │
│  └────────────┘ └───────────┘               │
└──────────────────────────────────────────────┘

## 9. Team Requirements

### 9.1 Phase-wise Team

| Role | Foundation | Alpha | Beta | Launch | Scale |
| --- | --- | --- | --- | --- | --- |
| Protocol Lead | 1 | 1 | 1 | 1 | 1 |
| Backend Engineer | 2 | 2 | 3 | 4 | 6 |
| Frontend Engineer | 0 | 1 | 2 | 2 | 3 |
| Security Engineer | 1 | 1 | 1 | 1 | 2 |
| DevOps | 0 | 1 | 1 | 2 | 3 |
| QA | 0 | 1 | 1 | 2 | 2 |
| Product Manager | 0 | 0 | 1 | 1 | 1 |
| Developer Relations | 0 | 0 | 1 | 2 | 3 |
| Business Development | 0 | 1 | 2 | 3 | 5 |
| Total | 4 | 8 | 13 | 18 | 26 |

## 10. Budget Estimation

### 10.1 Year 1 Budget

| Category | Q1 | Q2 | Q3 | Q4 | Total |
| --- | --- | --- | --- | --- | --- |
| Engineering (salaries) | $60K | $120K | $200K | $280K | $660K |
| Infrastructure | $600 | $2.4K | $9K | $24K | $36K |
| Legal (protocol, compliance) | $10K | $5K | $10K | $5K | $30K |
| Marketing | $0 | $2K | $10K | $30K | $42K |
| Business development | $0 | $5K | $10K | $15K | $30K |
| Tools & services | $2K | $5K | $8K | $10K | $25K |
| Total | $73K | $139K | $247K | $364K | $823K |

### 10.2 Revenue Model

| Revenue Stream | Launch (Monthly) | Scale Y2 (Monthly) |
| --- | --- | --- |
| Premium vendor listings | $1K | $20K |
| Verified badge fees | $500 | $10K |
| Transaction commission (1-3%) | $0 | $50K |
| Enterprise buyer subscriptions | $0 | $30K |
| API access (high-volume) | $0 | $15K |
| AVP Cloud (managed hosting) | $0 | $25K |
| Total | $1.5K | $150K |

## 11. Risk Mitigation

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Low vendor adoption | High | Critical | Personal onboarding, free premium tier, integration support |
| Security breach | Low | Critical | Security audits, bug bounty, penetration testing |
| Protocol too complex | Medium | High | Keep v1 minimal, iterate based on feedback |
| Competitor launches similar | Medium | Medium | First-mover advantage, community building, open-source moat |
| Funding runs out | Medium | Critical | Revenue model early, grants, VC if needed |
| Spam/abuse at scale | High | Medium | Rate limiting, verification requirements, abuse detection |
| Legal challenges | Low | High | Legal review of protocol, terms of service, compliance |

## 12. Success Metrics

### 12.1 North Star Metrics

| Metric | Month 6 | Month 12 | Month 24 |
| --- | --- | --- | --- |
| Proposals generated | 50 | 500 | 25,000 |
| Deals closed via AVP | 2 | 20 | 500 |
| Total deal value | $20K | $500K | $20M |

### 12.2 Operational Metrics

| Metric | Target |
| --- | --- |
| Discovery document uptime | 99.9% |
| Registry API uptime | 99.95% |
| Average proposal generation time | < 30 seconds |
| Average handshake time | < 500ms |
| Vendor onboarding time | < 30 minutes (self-service) |
| Business verification time | < 5 business days |
| Support response time | < 24 hours |

End of Go-Live Plan