# AVP - PROJECT-PLAN

# AVP Comprehensive Project Plan

Complete Project Plan with Phases, Milestones, Dependencies, and Deliverables

Version: 1.0-draft Date: 2026-03-18

## Table of Contents

- Executive Summary

- Project Scope

- Work Breakdown Structure

- Phase 1: Protocol & Foundation

- Phase 2: Core Development

- Phase 3: Alpha Network

- Phase 4: Beta Launch

- Phase 5: Public Launch

- Phase 6: Scale & Sustain

- Dependencies Map

- Risk Register

- Resource Plan

- Communication Plan

- Quality Assurance Plan

## 1. Executive Summary

AVP (AI Vendor Protocol) is an open-source protocol enabling AI-to-AI business communication across websites. This project plan covers the complete lifecycle from specification to scaled production.

Timeline: 18 months to full scale Budget: ~$1.2M (Year 1: 823K,Year2H1: 400K) Team: 4 → 26 people over 18 months Target: 15,000+ vendors, 10,000+ buyers by end of Year 2

## 2. Project Scope

### 2.1 In Scope

| Component | Description |
| --- | --- |
| Protocol Specification | Complete technical spec with formal grammar |
| Vendor SDK | Node.js, Python, Go implementations |
| Buyer SDK | Node.js, Python implementations |
| Chrome Extension | Buyer-facing browser extension |
| AVP Registry | Central discovery and indexing service |
| Trust Authority | Business verification and trust scoring |
| Web Dashboard | Buyer and vendor web interfaces |
| Documentation | Complete technical and user documentation |
| Website | Protocol website with docs, blog, community |
| Integrations | CRM, Slack, payment platform integrations |

### 2.2 Out of Scope (v1)

- Mobile native apps

- Payment processing / escrow

- Legal contract generation

- AI model training/fine-tuning

- Non-English documentation

## 3. Work Breakdown Structure

AVP Project
│
├── 1. Protocol & Specification
│   ├── 1.1 Core spec (discovery, handshake, RFP, proposal)
│   ├── 1.2 Negotiation spec (state machine, rounds)
│   ├── 1.3 Auth spec (Ed25519, JWT, sessions)
│   ├── 1.4 Trust spec (verification, scoring)
│   ├── 1.5 Error handling spec
│   ├── 1.6 JSON Schema definitions
│   └── 1.7 OpenAPI specification
│
├── 2. Core Infrastructure
│   ├── 2.1 Registry service
│   ├── 2.2 Trust authority service
│   ├── 2.3 Search service
│   ├── 2.4 Webhook service
│   ├── 2.5 Auth service
│   ├── 2.6 Database schema & migrations
│   └── 2.7 CI/CD pipeline
│
├── 3. SDKs & Libraries
│   ├── 3.1 Vendor SDK (Node.js)
│   ├── 3.2 Vendor SDK (Python)
│   ├── 3.3 Vendor SDK (Go)
│   ├── 3.4 Buyer SDK (Node.js)
│   ├── 3.5 Buyer SDK (Python)
│   ├── 3.6 Common crypto library
│   └── 3.7 Schema validation library
│
├── 4. Client Applications
│   ├── 4.1 Chrome extension
│   ├── 4.2 Buyer web dashboard
│   ├── 4.3 Vendor web dashboard
│   ├── 4.4 Admin panel
│   └── 4.5 Embeddable widget
│
├── 5. Integrations
│   ├── 5.1 Slack integration
│   ├── 5.2 Salesforce integration
│   ├── 5.3 HubSpot integration
│   ├── 5.4 Stripe/Razorpay integration
│   ├── 5.5 WordPress plugin
│   └── 5.6 Email integration
│
├── 6. Documentation & Website
│   ├── 6.1 Protocol documentation
│   ├── 6.2 API reference
│   ├── 6.3 SDK guides
│   ├── 6.4 Tutorials
│   ├── 6.5 Website (avp-protocol.org)
│   └── 6.6 Blog
│
├── 7. Security
│   ├── 7.1 Security audit
│   ├── 7.2 Penetration testing
│   ├── 7.3 Bug bounty program
│   └── 7.4 Compliance (SOC 2 prep)
│
└── 8. Community & Growth
    ├── 8.1 Vendor onboarding program
    ├── 8.2 Developer relations
    ├── 8.3 Marketing & launch
    ├── 8.4 Community management
    └── 8.5 Partnerships

## 4. Phase 1: Protocol & Foundation (Weeks 1-6)

### 4.1 Milestone: Protocol Specification Complete

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Draft core protocol spec | 2 weeks | None | Protocol Lead |
| Draft auth specification | 1 week | Core spec | Security Lead |
| Draft trust specification | 1 week | Core spec | Protocol Lead |
| Define JSON schemas | 1 week | All specs | Protocol Lead |
| Write OpenAPI spec | 1 week | JSON schemas | Backend Lead |
| Peer review (internal) | 1 week | All above | Team |

### 4.2 Milestone: Development Environment Ready

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Set up GitHub org + repos | 1 day | None | DevOps |
| Configure CI/CD | 2 days | GitHub org | DevOps |
| Set up AWS staging | 3 days | None | DevOps |
| Database schema design | 1 week | Protocol spec | Backend Lead |
| Set up local dev environment | 3 days | All above | DevOps |
| Register avp-protocol.org | 1 day | None | Admin |

### 4.3 Deliverables

- Published protocol specification (v1.0-draft)

- JSON Schema files for all message types

- OpenAPI specification

- GitHub organization with all repos

- CI/CD pipeline operational

- Local development environment (Docker Compose)

## 5. Phase 2: Core Development (Weeks 7-16)

### 5.1 Milestone: Vendor SDK v0.1

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Core crypto library (Ed25519) | 1 week | Auth spec | Security Lead |
| Discovery document publisher | 1 week | Protocol spec | Backend Dev 1 |
| Handshake handler | 1 week | Crypto library | Backend Dev 1 |
| RFP handler | 2 weeks | Handshake | Backend Dev 1 |
| Proposal response builder | 1 week | RFP handler | Backend Dev 1 |
| Schema validation middleware | 1 week | JSON schemas | Backend Dev 2 |
| Express.js middleware | 1 week | All above | Backend Dev 1 |

### 5.2 Milestone: Buyer SDK v0.1

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Discovery client | 1 week | Protocol spec | Backend Dev 2 |
| Handshake client | 1 week | Crypto library | Backend Dev 2 |
| RFP sender | 1 week | Handshake client | Backend Dev 2 |
| Proposal collector | 1 week | RFP sender | Backend Dev 2 |
| AI analysis integration | 2 weeks | Proposal collector | Backend Dev 2 |

### 5.3 Milestone: Registry Service v0.1

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Agent registration API | 1 week | DB schema | Backend Dev 2 |
| Search API | 2 weeks | Registration | Backend Dev 2 |
| Trust score storage | 1 week | Registration | Backend Dev 1 |
| Health monitoring | 1 week | Registration | DevOps |

### 5.4 Milestone: End-to-End Flow Working

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Integration testing | 2 weeks | All SDKs + Registry | QA |
| Bug fixes from integration | 1 week | Integration testing | Team |
| Performance baseline | 3 days | Bug fixes | DevOps |

### 5.5 Deliverables

- Vendor SDK v0.1 (npm published)

- Buyer SDK v0.1 (npm published)

- Registry service deployed (staging)

- End-to-end: discover → handshake → RFP → proposal working

- Integration test suite (>80% coverage)

## 6. Phase 3: Alpha Network (Weeks 17-26)

### 6.1 Milestone: First 10 Vendors Live

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Vendor onboarding portal | 2 weeks | Registry v0.1 | Frontend Dev |
| Vendor outreach (20 targets) | 3 weeks | SDKs | Biz Dev |
| Assisted integration support | 4 weeks | SDKs | Backend Lead |
| Python vendor SDK | 3 weeks | Core spec stable | Backend Dev 2 |
| Vendor dashboard (basic) | 3 weeks | Registry API | Frontend Dev |

### 6.2 Milestone: First Real Transactions

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Negotiation state machine | 2 weeks | Core flow | Backend Dev 1 |
| Counter-proposal handling | 1 week | State machine | Backend Dev 1 |
| Settlement flow | 1 week | Negotiation | Backend Dev 1 |
| Buyer dashboard (basic) | 3 weeks | Buyer SDK | Frontend Dev |
| First 5 real RFP cycles | 4 weeks | All above | Biz Dev |

### 6.3 Milestone: Trust System v1

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Domain verification | 2 weeks | Registry | Backend Dev 2 |
| Business doc upload/storage | 1 week | Registry | Backend Dev 2 |
| AI document extraction | 2 weeks | Doc upload | Backend Dev 2 |
| Trust score calculator | 2 weeks | Transaction data | Backend Dev 1 |
| Human review workflow | 1 week | All above | Backend Dev 2 |

### 6.4 Deliverables

- 10+ vendors with live agents

- Python vendor SDK published

- Vendor + buyer dashboards (basic)

- Negotiation flow working

- Trust system operational

- 5+ real RFP-to-proposal cycles completed

- Protocol spec updated based on alpha feedback

## 7. Phase 4: Beta Launch (Weeks 27-38)

### 7.1 Milestone: Chrome Extension Beta

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Extension architecture | 1 week | Buyer SDK | Frontend Dev 2 |
| Search UI | 2 weeks | Architecture | Frontend Dev 2 |
| Results display | 1 week | Search UI | Frontend Dev 2 |
| Notification system | 1 week | Results | Frontend Dev 2 |
| Settings/preferences | 1 week | Notifications | Frontend Dev 2 |
| Chrome Web Store prep | 1 week | All above | Frontend Dev 2 |

### 7.2 Milestone: Self-Service Onboarding

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Self-service registration flow | 2 weeks | Registry v1 | Frontend Dev |
| Automated domain verification | 1 week | Verification system | Backend Dev 2 |
| Guided SDK integration wizard | 2 weeks | SDKs stable | Frontend Dev |
| Documentation site (Docusaurus) | 3 weeks | All docs | DevRel |

### 7.3 Milestone: Integrations

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Webhook delivery system | 2 weeks | Core events | Backend Dev 1 |
| Slack integration | 1 week | Webhooks | Backend Dev 2 |
| Email notifications | 1 week | Webhooks | Backend Dev 2 |
| Salesforce integration | 2 weeks | Webhooks | Backend Dev 1 |
| HubSpot integration | 1 week | Webhooks | Backend Dev 1 |

### 7.4 Milestone: Proposal Comparison AI

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| AI ranking algorithm | 2 weeks | Proposal data | AI/ML Dev |
| Side-by-side comparison UI | 2 weeks | Ranking | Frontend Dev |
| Recommendation engine | 2 weeks | Ranking | AI/ML Dev |

### 7.5 Deliverables

- Chrome extension in beta (invite-only)

- Self-service vendor onboarding

- Slack + CRM integrations live

- AI-powered proposal comparison

- 50+ vendors, 20+ buyers

- Documentation site live

## 8. Phase 5: Public Launch (Weeks 39-48)

### 8.1 Milestone: Production Ready

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Security audit | 3 weeks | All components | External firm |
| Performance testing | 2 weeks | All components | QA + DevOps |
| Load testing (10K concurrent) | 1 week | Performance baseline | DevOps |
| Disaster recovery testing | 1 week | Infrastructure | DevOps |
| SOC 2 preparation | 4 weeks | All security measures | Security Lead |

### 8.2 Milestone: Public Launch

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Chrome extension on Web Store | 1 week | Security audit pass | Frontend Dev 2 |
| Public registry launch | 1 week | Security audit pass | DevOps |
| WordPress plugin | 3 weeks | Vendor SDK stable | Backend Dev |
| Embeddable widget | 2 weeks | Cloud-hosted agent | Frontend Dev |
| Launch marketing | 4 weeks | All above | Marketing |
| Product Hunt launch | 1 day | Marketing prep | Marketing |

### 8.3 Milestone: Monetization Pilot

| Task | Duration | Dependencies | Owner |
| --- | --- | --- | --- |
| Premium listing system | 2 weeks | Registry v2 | Backend Dev |
| Payment integration (Stripe) | 2 weeks | Premium system | Backend Dev |
| Subscription management | 1 week | Payment | Backend Dev |
| Revenue dashboard | 1 week | All above | Frontend Dev |

### 8.4 Deliverables

- Security audit passed

- Chrome extension public on Web Store

- Public registry with 500+ vendors

- WordPress plugin published

- Revenue generation started

- Press coverage secured

## 9. Phase 6: Scale & Sustain (Months 13-24)

### 9.1 Key Initiatives

| Initiative | Timeline | Target |
| --- | --- | --- |
| Go SDK | Month 13-15 | Enterprise adoption |
| Regional registries (EU, India) | Month 14-17 | Data compliance |
| Advanced AI negotiation | Month 15-18 | Better outcomes |
| Mobile app (React Native) | Month 16-20 | Wider reach |
| Enterprise tier | Month 17-19 | Revenue growth |
| API marketplace | Month 18-22 | Ecosystem growth |
| IETF Internet-Draft | Month 20 | Standardization |
| Industry partnerships | Ongoing | Network growth |

## 10. Dependencies Map

Protocol Spec
    │
    ├───▶ JSON Schemas ───▶ Schema Validation Library
    │                              │
    ├───▶ Auth Spec ──────▶ Crypto Library
    │                        │
    │                        ├───▶ Vendor SDK ──────┐
    │                        │                       │
    │                        └───▶ Buyer SDK ────────┤
    │                                                │
    ├───▶ DB Schema ──────▶ Registry Service ────────┤
    │                              │                  │
    │                              ├───▶ Trust Service│
    │                              │                  │
    │                              └───▶ Search ──────┤
    │                                                 │
    └───▶ OpenAPI ────────▶ Documentation ────────────┤
                                                      │
                          Chrome Extension ◀───────────┤
                          Web Dashboards ◀─────────────┤
                          Integrations ◀───────────────┘

### 10.1 Critical Path

Protocol Spec → Crypto Library → Vendor SDK → End-to-End Flow → Alpha → Beta → Launch

Any delay in the critical path delays the entire project.

## 11. Risk Register

| # | Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | Low vendor adoption | High | Critical | Personal outreach, free premium, integration support | Biz Dev |
| R2 | Security vulnerability found post-launch | Medium | Critical | Pre-launch audit, bug bounty, rapid response plan | Security |
| R3 | Protocol too complex for adoption | Medium | High | Keep v1 minimal, developer experience focus | Protocol Lead |
| R4 | Key team member leaves | Medium | High | Document everything, no single points of failure | PM |
| R5 | Funding insufficient | Medium | Critical | Revenue model early, phased spending, grant applications | Admin |
| R6 | Competing standard emerges | Low | High | First-mover advantage, community building, open governance | All |
| R7 | Legal challenge to automated negotiation | Low | Medium | Legal review, clear terms of service, human-in-the-loop | Legal |
| R8 | Scale challenges (10K+ agents) | Medium | Medium | Cloud-native architecture, load testing early | DevOps |
| R9 | AI hallucination in proposals | High | Medium | Structured data (not free-text), validation, human review flags | AI/ML |
| R10 | Spam/abuse overwhelms network | High | Medium | Rate limiting, verification requirements, anomaly detection | Security |

## 12. Resource Plan

### 12.1 Team Ramp

Month:    1    3    6    9    12   18   24
Team:     4    6    10   15   18   22   26
          │    │    │    │    │    │    │
Roles:    │    │    │    │    │    │    │
Backend:  2    2    3    4    4    5    6
Frontend: 0    1    2    2    2    3    3
Security: 1    1    1    1    1    2    2
DevOps:   0    1    1    2    2    2    3
QA:       0    0    1    1    2    2    2
Product:  0    0    0    1    1    1    1
DevRel:   0    0    1    1    2    2    3
BizDev:   0    1    1    2    3    4    5
Admin:    1    0    0    1    1    1    1

### 12.2 Key Hires Timeline

| Role | When | Priority |
| --- | --- | --- |
| Backend Engineer #2 | Month 1 | Critical |
| Security Engineer | Month 1 | Critical |
| Frontend Engineer | Month 3 | High |
| DevOps Engineer | Month 3 | High |
| Business Development | Month 4 | High |
| QA Engineer | Month 5 | Medium |
| Developer Relations | Month 6 | Medium |
| Product Manager | Month 7 | Medium |
| AI/ML Engineer | Month 7 | Medium |

## 13. Communication Plan

### 13.1 Internal Communication

| Channel | Frequency | Participants | Purpose |
| --- | --- | --- | --- |
| Daily standup | Daily | Engineering | Status, blockers |
| Sprint planning | Bi-weekly | Engineering + Product | Prioritization |
| Sprint review | Bi-weekly | All | Demo + feedback |
| Steering Committee | Monthly | SC members | Strategy, governance |
| All-hands | Monthly | Everyone | Vision, updates |

### 13.2 External Communication

| Channel | Frequency | Audience | Owner |
| --- | --- | --- | --- |
| Blog | Weekly | Developers, community | DevRel |
| Newsletter | Monthly | Subscribers | Marketing |
| GitHub Discussions | Ongoing | Contributors | Community |
| Discord | Ongoing | Community | Community |
| Twitter/LinkedIn | Daily | Public | Marketing |
| Release notes | Per release | Users | DevRel |

## 14. Quality Assurance Plan

### 14.1 Testing Strategy

| Test Type | Coverage Target | Automation |
| --- | --- | --- |
| Unit tests | 80%+ | Fully automated |
| Integration tests | All API endpoints | Fully automated |
| Contract tests | All AVP message types | Fully automated |
| End-to-end tests | Critical paths | Automated (Playwright) |
| Performance tests | P99 latency targets | Automated (k6) |
| Security tests | OWASP Top 10 | Automated (ZAP) + manual |
| Compatibility tests | All SDK versions | Automated |

### 14.2 Definition of Done

Every feature must:

- Pass all automated tests

- Have code review from 1+ reviewer

- Have documentation (if user-facing)

- Pass schema validation

- Meet performance targets

- Have no known security issues

- Work across all supported SDK versions

### 14.3 Release Process

Feature Branch
    │
    ├── PR created
    │   ├── CI passes (lint, test, build)
    │   ├── Code review approved
    │   └── Schema validation passes
    │
    ├── Merged to main
    │   ├── Staging deployment (auto)
    │   ├── Integration tests (auto)
    │   └── Performance tests (auto)
    │
    └── Release
        ├── Changelog generated
        ├── Version bumped
        ├── Production deployment
        ├── Smoke tests
        └── Announcement

End of Project Plan